Coordinated Investment Governance

Background

All ecosystem change occurs through local action.  That local action is empowered or disempowered by interdependent local-state-federal systems.  Local actors are positioned to identify improvements to that system.  These improvements can improve the efficacy of state and federal programs.  Only state and federal managers can reorganize resources to improve the ecosystem management operating environment.  Integrated local solutions supported by diverse programs provide more benefit at lower public cost.  An ad hoc Coordinated Investment Steering Committee was organized to identify these solutions by consulting with an integrated local consortium.  That committee agreed that improvement projects, identified in the field, need to become part of our operations, and will have the greater likelihood of impact if they are conducted publically.

Current Situation and Problem

Existing committees and boards form around appropriations and therefore reinforce stovepipes. There are no mechanisms by which an integrated local consortium can evaluate problems and implement solutions that affect the regional or national programs that affect the ecosystem management operating environment.

Root Cause Analysis

- There is very limited capacity empowered to conduct systems analysis and problem solving among the different strata and silos of government.

- There is no pressure or reward for agencies to act on systemic problems that emerge through the cumulative implementation of programs.

- Legislators and executives often don’t understand the ecosystem management operating environment experienced by field practitioners.

- (links back to 1… feedback loop)

Value Proposition and Metrics

We will create a cross-agency system by which integrated local consortia can make proposals to improve the ecosystem management operating environment.  This will create a feedback loop that enables us to make small and thoughtful adaptations to maximize our use of existing agency resources. Using existing boards and councils reduces the cost of coordination, and enhances the power of existing forums by increasing information flow from the field.

Metric:  Number of Improvement Projects Completed

Objectives

- Local consortia form to work with agency field staff to identify ways to improve the ecosystem management operating environment.

- Governor’s Results Washington Goal #3 Council – Sustainable Energy and a Clean Environment (RW) refines and adopts projects that affect state agency operations.

- The Puget Sound Federal Task Force (FTF) refines and adopts projects that affect federal agency operations.

- The Puget Sound Ecosystem Coordination Board (ECB) is notified by the local consortium and serves as the advocate for improvements to interdependent local-state-federal systems.

- Volunteer staff, starting with NOAA, PSP, TNC and Snohomish County support development of improvement projects.

- Each agency identifies a point of contact that is positioned to vet improvement project issues across agency silos.

- This system will be tested through the implementation of three improvement projects defined through the Snohomish Pilot Effort.

Action Plan

| # | Task/Deliverable | Purpose | Status |
| --- | --- | --- | --- |
| 1 | Complete CI transmittal memo | Initiate formal request from ILC | Waiting for #3 |
| 2 | Delivery of CI proposals in FTF workplan | CI proposals are included in Puget Sound Federal Task Force work plan. | Complete. Regulatory coordination adopted with reduced specificity. |
| 3 | Plan for engaging RW, FTF, ECB, and LIO | Chair and staff of each board agree to process for engagement | Underway |
| 4 | Web-based tracking system | Web page contains up to date information on project status. | Waiting for #3 |
| 5 | Initial contact with RW, FTF, ECB | Coordinated investment proposals and processes have been ratified by each board. | RW: March 13 FTF: TBD ECB: March 3 |
| 6 | Brief SRC, Watershed Leads, Conservation Commission, SRFB. LIOs | Forums that support on-the-ground ecosystem restoration efforts are briefed on the coordinated investment governance model. | To be determined |
| 7 | Status reporting/problem solving | Resolve barriers, celebrate accomplishments | Waiting for #5 |

The local ecosystem management operating environment is affected by systems that result from interactions between local, state, and federal actors, but is not wholly controlled by any one actor, resulting in many unintentional dynamics.  Because legal and economic authority rests at the state and federal level.

The ecosystem management operating environment describes the conditions in which local actors attempt to change complex social-ecological systems.  Six elements have been identified that are required for ecosystem management, and that typically require the engagement of multiple actors: funding, labor, land access, social consensus, permitting, and knowledge.

Local ecosystem management actions typically emerge from a single interest group.  Integrated consortiums where diverse interest groups identify shared management strategies have increased political power, and are more likely to result in large scale ecosystem recovery.